## Slide 1
WEEKLY STATUS REPORT
START NOW

## Slide 2
Ongoing PROJECTS
IFRS9
CLIENT RISK RATING
  VENDOR: PIO-TECH
  BUSINESS OWNER: FALAH KOKASH
  PERCENT COMPLETE: 60 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: DELAYED
  KEY MILESTONES ACHIEVED: Provide Pio-Tech with a DB Link with DWH
  Action Item: Pio Tech Team to provide us with the reports to compare with Mr Falah files
  VENDOR: ICSFS-BANKS
  BUSINESS OWNER: SAHER ABDELHADI
  Percent Complete: 96 %
  Budget Status: on budget
  Timeline: on-track
  Key Milestones achieved: Sign-off
ACTION ITEM: ICS to correct: the below 3 fields:
  Internal transfer, mobile bank transactions, variance of salary transactions.
Project Name
GPI SUBSCRIPTION
  VENDOR: AEG & SWIFT
  BUSINESS OWNER: ADNAN ZAKARIA
  PERCENT COMPLETE: 100 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: Completed
  KEY MILESTONES ACHIEVED: Sign-off
  ACTION ITEM:
  VENDOR: .
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
Project Name
MT2ISO PROJECT
  VENDOR: AEG
  BUSINESS OWNER: ADNAN ZAKARIA
  PERCENT COMPLETE: 100 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: Completed
  KEY MILESTONES ACHIEVED: Go-Live
  ACTION ITEM: We have moved the converter to the live environment .
  VENDOR: .
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
GAS STATION
XPI PROJECT
  VENDOR: CBI
  BUSINESS OWNER: Bzhar Omar
  PERCENT COMPLETE: 100 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: on-track
  KEY MILESTONES ACHIEVED: Go-Live
  ACTION ITEM: Credentials received from CBI
  VENDOR: ICSFS-BANKS
  BUSINESS OWNER: SAHER ABDELHADI
  Percent Complete: 95 %
  Budget Status: on budget
  Timeline: on-track
  Key Milestones achieved: ongoing module
  ACTION ITEM:
ZENHR - PROJECT
Compliance PREDATOR
  VENDOR: GBG
  BUSINESS OWNER: Goran Burhan
  PERCENT COMPLETE: 95 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: ON-TRACK
  KEY MILESTONES ACHIEVED: COMPLETE THE TEST CASES and UAT for Stage and Dev
  ACTION ITEM: Waiting for management to decide to go to life. AFTER THAT WE WILL START THE GO-LIVE PHASE
  VENDOR: ZenHR
  BUSINESS OWNER: Dilshad Ali
  PERCENT COMPLETE: 95 %
  BUDGET STATUS: ON BUDGET
  TIMELINE: completed
  KEY MILESTONES ACHIEVED: Go-Live Activities
CENTRALIZED DATA WAREHOUSE – GAP ANALYSIS
PROCESS ENHANCEMENT
  VENDOR: In - House
  BUSINESS OWNER: Hazim Al-Tamimi
  PERCENT COMPLETE: 50%
  BUDGET STATUS: ON BUDGET
  TIMELINE: ON-TRACK
  KEY MILESTONES ACHIEVED: Detailed processes and capacity processes for all departments received.
  ACTION ITEM: Progressing on the development phase.
  VENDOR: Not defined yet
  BUSINESS OWNER: Hazim Al-Tamimi
  PERCENT COMPLETE: 25%
  BUDGET STATUS: ON BUDGET
  TIMELINE: On-Track
  KEY MILESTONES ACHIEVED: Gaps identification for all business functions within our bank.
  ACTION ITEM: Gaps resolution plan for all identified gaps.

## Slide 3
Ongoing PROJECTS
Call Center migration
FIB – PCI DSS Project (Al Ejabi)
  VENDOR:BMB
  BUSINESS OWNER: Jalal Burghul
  PERCENT COMPLETE: 95%
  BUDGET STATUS: ON BUDGET
  TIMELINE: On-Track
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
  VENDOR: ejabi
  BUSINESS OWNER: Mr. Ibrahim
  PERCENT COMPLETE: 2%
  BUDGET STATUS: ON BUDGET
  TIMELINE: On-Track
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
Project Name
Project Name
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
Project Name
Project Name
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
PEPs EY - Assessment
Project Name
  VENDOR: EY
  BUSINESS OWNER: Saher Abdelhadi
  PERCENT COMPLETE: 50%
  BUDGET STATUS: On Budget
  TIMELINE: On-Track
  KEY MILESTONES ACHIEVED: Compliance feedback covered the gaps within the PEPs EY report.
  ACTION ITEM: Developing controls, on the app. Based on the gaps of PEPs EY report.
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
Project Name
Project Name
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
Project Name
Project Name
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:
  VENDOR:
  BUSINESS OWNER:
  PERCENT COMPLETE:
  BUDGET STATUS:
  TIMELINE:
  KEY MILESTONES ACHIEVED:
  ACTION ITEM:

## Slide 4
XPI PROJECT
Project Manager :
11 January 2025

## Slide 5
PREDATOR PROJECT
Project Manager : Ali Zirak
26 th Nov 2025

## Slide 6
Project Highlights
PREDATOR PROJECT
Current Period
Previous Period
On Track
Last week The third round of Predator testing has been conducted by the Compliance team, and the related rules have been reviewed and tweaked based on the testing results. In parallel, the Windows Server license has been prepared and completed, supporting the environment readiness for the final testing activities.
Progress continues on the final Predator testing cycle required before go-live. The second roun
The System Admin team also increased the stage environment capacity by adding 8 additional cores. A final stress test will be conducted to evaluate the performance difference between the 16-core and 8-core environments. Following the completion of this stress test and the Compliance team’s confirmation that the alerts, rules, and operational process are ready, the team will proceed with go-live.
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks | Test finally from Compliance team | Completed | 25th May | Compliance Team / Abdulrahman.
Issues | Stresss test | Open | 3rd June | Abdulrahman Alhayk
Decisions | Go life for the week after that. |  |  | 
Reporting Period
26th May 2026 – 1st June 2026
Business Owner
Goran Burhan – Ibrahim Khalil
Project Manager
Ali Zirak
Key Risks, Issues, & Decisions
Planning
for training - SIT – UAT
Initiation and Requirements
Feb
Go-live
10th May
Hardware
Preparation
May
June
July
App Installation & SIT
May
Nov
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
UAT
Technical
and Business
Training
July
April

## Slide 7
Compliance – Predator
Key Action Items
Area | Action Item | Status | Due Date | Owner
 | Project Planning & Requirements finalizing | Completed | 28.March | GBG team
 | Specs Sign-Off | Completed | 13th April | FIB and GW team
 | Hardware Installation and testing | Completed | 6.May | Hazem Khalil
 | Predator & ML Installation | Complete | 28th. May | GBG Team - Luke Bargh
 | Planning the training and installation | Completed | 13th June 28th July | GBG Team - Mariya
 | System training | Completed | 1.June 28th July | GBG Team (Mariya, Vida, Luke)
 | SIT | Completed | 1.June 26th Nov | FIB and GW team
 | UAT | Delayed | 27th.June 30th March 10th June | FIB and GW team
 | Go-Live & Monitoring | Not started | 1.July 20th June | FIB team

## Slide 8
FIB – PCI DSS Project (Al Ejabi) PROJECT
Project Manager : Rudaw Abdulrahman

## Slide 9
Project Highlights
FIB – PCI DSS Project (Al Ejabi)
Current Period
Previous Period
On Track
Kick-off Meeting: Completed
Scope Definition: In Progress
Vendor Payment: In Progress
Gap Assessment started​;
Completed Network Architecture Review.
Completed Network Security Controls Review.
Next:Review of Application functions
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks | The CBI deadline is at risk because completing all pending network checks within one hour per week is unlikely to be enough, and the limited cadence is outside the PMO's control. | Open | 19th | FIB
Issues |  |  |  | 
Decisions |  |  |  | 
Reporting Period
June 9th 2026
Business Owner
Mr. Ibarihm
Project Manager
Rudaw Abdulrahman
On track
Delayed
At Risk
Implemented
On Hold
Terminated
On Track
Key Risks, Issues, & Decisions
Gap Assessment
Aug
Remediation
Apr – May June
Pre-Assessment
June
July
Initiation & Scoping
Formal Assessment
Apr

## Slide 10
FIB – PCI DSS Project (Al Ejabi)
Key Action Items
Area | Action Item | Status | Due Date | Owner
 | Initiation & Scope Definition | Completed | Apr | PM + IT Lead
 | Vendor Engagement & Payment (Al Ejabi) | In Progress | Apr | PM + Finance FIB
 | Gap Assessment | InProgress | June | Al Ejabi + FIB
 | Remediation Planning | Pending | June | FIB + IT Lead
 | Remediation Execution | Pending | June | IT Lead
 | Control Implementation | Pending | July | IT Lead + FIB
 | Pre-Assessment & Mock Audit | Pending | Aug | Al Ejabi + FIB
 | Formal PCI DSS Assessment | Pending | Aug | Al Ejabi
 | ROC, AOC & Project Closure | Pending | Aug | Al Ejabi + FIB

## Slide 11
Contact Center PROJECT
Project Manager : Rudaw Abdulrahman

## Slide 12
Project Highlights
Current Period
Previous Period
On Track
Project Status Update:
The contact center successfully live.
Eleveo installed — recorded audio is accessible.
this week done on track not updates
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks |  |  |  | 
Issues |  |  |  | 
Decisions |  |  |  | 
Reporting Period
June 19th, 2026
Business Owner
Jalal Burghol
Project Manager
Rudaw Abdulrahman
Key Risks, Issues, & Decisions
Requirements & Planning
Initiation
Jan
Go-live
April
On track
Delayed
At Risk
Implemented
On Hold
Terminated
Design and Build
Feb
UAT
Feb
Mar
Contact Center PROJECT
On Track

## Slide 13
Key Action Items
Area | Action Item | Status | Due Date | Owner
 | Online POC | completed | 27th feb | FIB
 | BRD approval | completed | 30th feb | FIB
 | Procurement process | completed | 5th March | FIB
 | Planning | completed | 5th March | PMO
 | Development | completed | 20th March | FIB
 | SIT testing | completed | 30th March | BMB & Newroz & FIB
 | UAT testing | completed | 14th April | BMB & Newroz & FIB
 | Go-live activities | completed | 14th April | FIB
Contact Center PROJECT

## Slide 14
ZENHR PROJECT
Project Manager : Rudaw Abdulrahman

## Slide 15
Project Highlights
Key Risks, Issues & Decisions
Reporting Date
March 30rd 2026
Business Owner
Omar Ayad
Prepared by
Rudaw Abdulrahman
Area | Item | Status | Due Date | Owner
Risks |  |  |  | 
Issues |  |  |  | 
Decisions |  |  |  | 
ZenHR Implementation – First Iraq Bank
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
Project Status update:
Project completed with condition; Payroll on Hold as per HR director request.
Key Risks, Issues, & Decisions
Requirements & Planning
Initiation
Jan-2025
Go-live
May July-2025
Design and Build
Feb-2025
UAT
Mar-2025
Apr
July-2025
Current Period
Previous Period
Completed
Completed
Apr-May
Apr-May
Payroll Module Test & live
March 2026

## Slide 16
ZenHR Implementation – First Iraq Bank
KEY ACTION ITEMS & MILESTONES – FIB-ZenHR Project
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
# | Action Item | Status | Due Date | Owner
1 | Online PoC | Completed | 25-Jan-2025 | ZenHR, FIB HR
2 | BRD Approval | Completed | 25-Jan-2025 | ZenHR, FIB HR
3 | Procurement Process | Completed | 9-Feb-2025 | FIB, GW
4 | Project Planning Finalization | Completed | 15-Feb-2025 | PMO
5 | System Configuration & Development | Completed | 23-Mar-2025 | ZenHR, FIB HR
6 | SIT Testing (System Integration Testing) | Completed | 24th July 2025 | ZenHR, FIB HR
7 | UAT Testing (User Acceptance Testing) | Completed | 24th July 2025 31st July 2025 | ZenHR, FIB HR
8 | Go-Live Activities | Completed | 24th July 2025 31st July 2025 | ZenHR, FIB HR
9 | Go-Live Payroll | Rejected | 1st March 2026 | ZenHR, FIB HR

## Slide 17
PROCESS ENHANCEMENT and Automation
Project Manager : Ezzat Zalzala
9th June 2026

## Slide 18
Project Status Update: Progressing still on the development phase for most of the departments. We already had meetings for Treasury, Branches, Credits, Risks, Cards, HR and for Operations. Tickets are opened on Jira and are being updated daily. Already started for CBI reports to be automated with Credits, Risks and Finance and we are starting to validate those reports to start the implementation through Jira with Ms. Sara and Mr. Mohammed. Audits, compliance and ICD are already added into the project for automation.
Project Highlights
Process Enhancement and Automation
Current Period
Previous Period
On Track
Key Risks, Issues & Decisions
Reporting Period
2nd June 2026–9th June 2026
Business Owner
Hazem Al-Tamimi
Project Manager
Ezzat Zalzala
Key Risks, Issues, & Decisions
Business Requirements
Collection
Collect & Review current
processes
September, October (2025)
Development
November, December (2025),
January, March, April (2026)
Go- Live
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
User Acceptance
Testing
Area | Item | Status | Due Date | Owner
Risks | No risks identified- currently |  |  | 
Issues | No issues identified- currently |  |  | 
Decisions |  |  |  | 
March, April, May, June (2026),
August 2026
September 2026

## Slide 19
Key Action Items
Process Enhancement and Automation
# | Action Item | Status | Due Date | Owner
1 | Review Current Processes | Completed | 5.10.2025 12.10.2025 1.12.2025 | ICD and PMO
2 | Business Requirement Documents | Completed | 9.10.2025 16.10.2025 28.10.2025 6.11.2025 30.11.2025 15.12.2025 31.12.2025 15.1.2026 31.3.2026 | ICD and PMO
3 | Development | In Progress | 31.5.2026 30.6.2026 | ICD, PMO, IT
4 | Quality and Procedures Validations | Not Started |  | PMO, Quality and Procedures
5 | User Acceptance Testing | Not Started |  | PMO, Development
6 | Go-Live | Not Started |  | PMO, Development

## Slide 20
Centralized data Warehouse Project
Project Manager : Ezzat Zalzala
9th June 2026

## Slide 21
Project Status Update: All tickets related to Kaka Goran team are on hold, while the remaining tickets are progressing.
Project Highlights
Centralized Data Warehouse – Gap Analysis – Phase I
Current Period
Previous Period
On Track
Key Risks, Issues & Decisions
Reporting Period
2nd June. 2026– 9thJune 2026
Business Owner
Hazem Al-Tamimi
Project Manager
Ezzat Zalzala
Key Risks, Issues, & Decisions
Initiation & setting
Requirements
Kick off
Gap Analysis – Phase I
February
Gaps Identifications
Phase II – Implementation
& Training
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
Remedy Plan
Area | Item | Status | Due Date | Owner
Risks | No risks identified- currently |  |  | 
Issues | No issues identified- currently |  |  | 
Decisions |  |  |  | 
July
March , April, May June (2026)
Unknown
March

## Slide 22
Key Action Items
Centralized Data Warehouse – Gap Analysis – Phase I
# | Action Item | Status | Due Date | Owner
1 | Data Landscape Assessment | Completed | 6.4.2025 | Beye
2 | Data Quality Assessment | Completed | 6.4.2025 | Beye
3 | Business Requirements Alignment (KPIs And reports per department) | Completed | 22.5.2025 29.5.2025 | Beye, FIB, GW
4 | GL Gaps Identification | Completed | 22.7.2025 | Beye
5 | MIS Gaps Identification | Completed | 22.7.2025 | Beye
6 | GL Remedy Plans (The recommendations To resolve GL Gaps) | In progress | 31.5.2026 30.6.2026 | GW, FIB
7 | MIS Remedy Plans (The recommendations To resolve MIS Gaps) | In progress | 31.5.2026 30.6.2026 | GW,FIB

## Slide 23
GAS STATION PROJECT - Public
Project Manager : Ezzat Zalzala
9th June 2026

## Slide 24
Project Status Update: As per last discussions with the CBI, we will have to do the re-test again for the public gas stations. Awaiting Kaka Bzhar for the set up to discuss it again with CBI. A letter already sent to the CBI for the re-test of public gas stations and requiest project initiation for the private gas stations.
Project Highlights
Gas Station - Public
Current Period
Previous Period
On Track
Key Risks, Issues & Decisions
Reporting Period
2nd June. 2026 –9th June 2026
Business Owner
Bzhar Omar
Project Manager
Ezzat Zalzala
Key Risks, Issues, & Decisions
January (2026)
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
Area | Item | Status | Due Date | Owner
Risks | No risks identified- currently |  |  | 
Issues | No issues identified- currently |  |  | 
Decisions |  |  |  | 
Project Kick-off
Requirements & Planning
Set-up and Configurations
UAT
Go-Live
February
February
February
March, April (2026)

## Slide 25
Key Action Items
Gas Station - Public
# | Action Item | Status | Due Date | Owner
1 | Project Kick-off | Completed | 19.1.2026 | Payments, PMO, XPI
2 | Setting up the Requirements for the configuration files | Completed | 20.1.2026 | Payments, PMO, XPI
3 | Configuration files | Completed | 25.1.2026 | XPI
4 | Development & Configuration testing | Completed | 10.2.2026 | Payments, Cards
5 | Certification | Completed | 18.2.2026 26.2.2026 | PMO
6 | Go-Live & Stabilization | Completed | 1.3.2026 10.3.2026 20.3.2026 31.3.2026 10.4.2026 21.4.2026 30.6.2026 | PMO, Payments, Cards

## Slide 26
PEPs EY – Assessment
Project Manager : Ezzat Zalzala
9thJune 2026

## Slide 27
Project Status Update: Following to our meeting on 8th of June 2026, the Risk Rating Mechanism, API integration, KYC updates and customer PEP self-update functionality remain outstanding and are expected to exceed their current target dates. The original development deadline was set for 15 June; however, due to dependencies on external vendors, a definitive timeline cannot yet be confirmed. While the Development team continues to prioritize these initiatives and is actively following up with the relevant vendors, the delivery schedule remains subject to external factors beyond the team's direct control.
Project Highlights
PEPs EY- Assessment
Current Period
Previous Period
On Track
Key Risks, Issues & Decisions
Reporting Period
2nd June. 2026 –9th June 2026
Business Owner
Saher Abdelhadi
Project Manager
Ezzat Zalzala
Key Risks, Issues, & Decisions
April (2026)
Completed
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
Area | Item | Status | Due Date | Owner
Risks | Kaka Khalid lost his son and we had to postpone the meeting for 1 week which added delay to the project | Resolved |  | Khalid Tawfeeq
Issues | No issues identified- currently |  |  | 
Decisions |  |  |  | 
Project Kick-off
Compliance Controls
Development Controls
May (2026)
June (2026)

## Slide 28
Key Action Items
Gas Station
# | Action Item | Status | Due Date | Owner
1 | Project Kick-off | Completed | 15.4.2026 | Compliance, PMO
2 | Compliance Requirements to cover the gaps within the PEPS EY Report | Completed | 25.4.2026 | Compliance
3 | Development controls on the app for the gaps defined within the PEPs EY report. | In Progress | 15.6.2026 | Development

## Slide 29
THANK YOU
FOR ATTENTION
11 January 2025

## Slide 34
GPI PRO PROJECT
Project Manager : ALAA AL-SMADI
06 January 2025

## Slide 35
Project Highlights
Current Period
Previous Period
On Track
Project Status Update: We have moved the GPI to live production and now we are testing the GPI observer with SWIFT team
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks | No risks identified- currently |  |  | 
Issues | No issues identified- currently |  |  | 
Decisions |  |  |  | 
Reporting Period
05 April 2026– 09 April 2026
Business Owner
Adnan Zakaria
Project Manager
Alaa Al-Smadi
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
GPI PRO PROJECT
Go-live
Phase
Preparation
Phase
Initiation
Phase
UAT
Phase
Training
Phase
February
April
September
October
December

## Slide 36
CLIENT RISK PROJECT
Project Manager : ALAA AL-SMADI
06 January 2025

## Slide 37
Project Highlights
Current Period
Previous Period
On Track
Project Status Update: Waiting Mr. Abdulrahman Alhayek to provide the IT a sample domestic transfer.
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks |  |  |  | 
Issues | We are working on the business comments after the go live |  |  | 
Decisions |  |  |  | 
Reporting Period
05 April 2026– 09 April 2026
Business Owner
Saher Abdelhadi
Project Manager
Alaa Al-Smadi
On Track
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
Client Risk Rating PROJECT
Sign-Off
Phase
Preparation
Phase
Initiation
Phase
UAT Onboarding
UAT
ongoing
December
February
July
September
April
December
Go-Live
Phase

## Slide 38
IFRS9 PROJECT
Project Manager : ALAA AL-SMADI
06 January 2025

## Slide 39
Project Highlights
Current Period
Previous Period
On Delay
Project Status Update: We are waiting Pio-Tech Team to provide us with grouping and staging files to compare with Mr. Falah files
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks | To be filled |  |  | 
Issues | To be filled |  |  | 
Decisions | To be filled |  |  | 
Reporting Period
05 April 2026– 09 April 2026
Business Owner
Falah Kokash
Project Manager
Alaa Al-Smadi
On Delay
On track
Delayed
At Risk
Implemented
On Hold
Terminated
InProgress
Not Started
IFRS9 PROJECT
Sign-Off
Phase
Preparation
Phase
Initiation
Phase
Integration
With CBS
UAT
Phase
Feb 2024
March 2024
July 2024
December
-
-
Go-Live
Phase

## Slide 40
Project Highlights
Lorem lorem default
Current Period
Previous Period
On Track
Lorem lorem
Lorem lorem
Key Risks, Issues & Decisions
Area | Item | Status | Due Date | Owner
Risks |  |  |  | 
Issues |  |  |  | 
Decisions |  |  |  | 
Reporting Period
12.Feb2025
Business Owner
Lorem lorem
Project Manager
lorem
Key Risks, Issues, & Decisions
Planning
Initiation and Requirements
Feb
Go-live
TBD
On track
Delayed
At Risk
Implemented
On Hold
Terminated
On Hold
Procurement
Feb
Installation & UAT
TBD
TBD

## Slide 41
Lorem lorem
Key Action Items
Area | Action Item | Status | Due Date | Owner
 | Project Planning & Requirements finalizing | In Progress | 30.Feb | GW Management
 | Vendor Selection & Procurement | Pending | TBD | GW Management
 | Regulatory & Compliance Approvals | Pending | TBD | 
 | Infrastructure & Integration Readiness |  |  | 
 | Software & System Integration |  |  | 
 | Deployment & Configuration |  |  | 
 | Testing & User Acceptance |  |  | 
 | Go-Live & Monitoring |  |  | 
 | Customer Awareness & Training |  |  |