## Dashboard
Project Owner | # of Projects | Projects (Completion Rate) | All Projects Avg Completion %
Waael Al-Qadhi | 8 | XPI Project (90%) ATM Project (10%) الاصلاح المصرفي (50%) Auto Settlement Requirement – CBI Mandate (100%) Connection With Meps (10%) FIB ISO Audits Reports (100%) POC - Cash withdrawal (5%) PEPS - EY assessment (5%) | 46.25%
Ezzat Zalzala | 4 | Gas Station (80%) Process Enhancement and Automation (50%) Centralized data warehouse - Gap Analysis (25%) Gas Station (100%) | 63.75%
Alaa Al-Smadi | 8 | Bank-BI Solution including (DWH, FATCA, BankCM, IFRS9, R.R) (65%) GPI Pro (95%) Client Risk Rating (90%) Regulatory Compliance Management (RCM) (TBD) Reconciliation System (5%) ERP Project (5%) MT2ISO (100%) AML Translator (100%) | 65.71%
Rudaw Abdulrahman | 3 | FIB – PCI DSS Project (Al Ejabi)​ (18%) Call Center migration (99%) ZenHR implementation (100%) | 72.33%
Ali Zirak | 1 | Compliance Predator (95%) | 95%

## Projects list
Project Name | Project Status | Project Jira Link | Complition Rate | Start Date | End Date | Priority | Project Manager | Comments | Paid | Remaining | Annual License | Column1
XPI Project | Ongoing |  | 90% |  |  | High | Waael Al-Qadhi | Status Update: 3-SOP is under completion from Nasreen. 4- PGW suspended, DR under reviwe, PCI in progress
ATM Project | To Be Started |  | 10% |  |  | Medum | Waael Al-Qadhi | Awaiting for Gov. Approval to start distributing the ATMs | 158215 | 0 | 0
الاصلاح المصرفي | in progress | https://fibtask.atlassian.net/browse/FIBTMP | 50% |  |  | High | Waael Al-Qadhi | In progress ( progressive elaboration)
Auto Settlement Requirement – CBI Mandate | Completed |  | 100% |  |  |  | Waael Al-Qadhi | Completed
Connection With Meps | on hold |  | 10% |  |  | Medum | Waael Al-Qadhi | subjected to migration timing
XPI -DR |  |  | 10% |  |  |  |  | awaiting Mr. Ibrahim feedback
Soft Pos |  |  | 100% |  |  |  |  | Going on cloud , working on PCI , we got the CBI approval
XPI Maigration | on going |  | 10% |  |  | High |  | Testing regarding infinite cards.
QR-International | Inititiation | https://fibtask.atlassian.net/browse/FIBQPR | 10% |  |  |  |  | Preparing approving the LOI
FIB ISO Audits Reports | Completed |  | 100% |  |  | Medum | Waael Al-Qadhi | successful renewal of all three ISO certifications (ISO 27001, ISO 22301, and ISO 20000).
POC - Cash withdrawal | Inititiation |  | 5% | 2026-01-05 |  | High | Waael Al-Qadhi | to complete the BRD, Planning, waiting kak. Aland direction
Gas Station | Ongoing | https://fibtask.atlassian.net/browse/FIBXPI-749 | 80% | 13.1.2026 | TBD | Medium | Ezzat Zalzala | The project re-opened to do re-test again. |  |  |  | The project re-opened again to do re-test
[9 empty] | Paid | Remaining | Annual License
Bank-BI Solution including (DWH, FATCA, BankCM, IFRS9, R.R) | Ongoing | https://fibtask.atlassian.net/jira/software/c/projects/FIBIFRS/boards/105?atlOrigin=eyJpIjoiYjlkOWU2MmU0YjFmNDUxY2IzMWY3MTZiMjcwNGE5NTAiLCJwIjoiaiJ9 | 65% | 30.01.2024 | TBD | Medum | Alaa Al-Smadi | Waiting Kak. Ali Othman to fix the issue in the database that has been raised by Pio-Tech | 161000 | 24000 | 29000 | Waiting Kak. Ali Othman to fix the issue in the database that has been raised by Pio-Tech
GPI Pro | Completed | https://fibtask.atlassian.net/browse/FIBCRR-130?atlOrigin=eyJpIjoiYmJiNDFjOTc1NGE3NDQ3Mzg5OGUzOTMzNDIzZjBiMjYiLCJwIjoiaiJ9 | 95% | Completed | Completed | Medum | Alaa Al-Smadi | We have moved the GPI to live production and now we are testing the GPI observer with SWIFT team | 13800 | 9200 | 8000 | We have moved the GPI to live production and now we are testing the GPI observer with SWIFT team
Client Risk Rating | Ongoing | https://fibtask.atlassian.net/browse/FIBCRR-26?atlOrigin=eyJpIjoiODc4ZGM1YzJmMmUyNDBhY2E5ZGIzZDE4ZTk3NWVjMjEiLCJwIjoiaiJ9 | 90% | 17.12.2024 |  | Medum | Alaa Al-Smadi | Waiting Mr. Abdulrahman Alhayek to provide the IT a sample domestic transfer. | 49000 | 0 | 8820 | ​ Waiting Mr. Abdulrahman Alhayek to provide the IT a sample domestic transfer.
Regulatory Compliance Management (RCM) | To be Started | TBD | TBD | TBD | TBD | Medum | Alaa Al-Smadi | We have finalized the contract and waiting the stakeholders to confirm the availability to proceed with the kick-off meeting | TBD | TBD | TBD | We have finalized the contract and waiting the stakeholders to confirm the availability to proceed with the kick-off meeting
Reconciliation System | To be Started | https://fibtask.atlassian.net/browse/FIBCRR-123?atlOrigin=eyJpIjoiZDNiMTE1YmFmNWQ2NDY1OTk3NTE1NWNiNTMzMjFkODYiLCJwIjoiaiJ9 | 5% | TBD | TBD | Medum | Alaa Al-Smadi | In the vendor evaluation phase. | TBD | TBD | TBD | In the vendor evaluation phase.
ERP Project | To be Started | https://fibtask.atlassian.net/browse/FIBCRR-164?atlOrigin=eyJpIjoiZmJjMmU0NTNiZjcyNDdjM2IyNjE3ZDg0MGU1NjE4NGYiLCJwIjoiaiJ9 | 5% | TBD | TBD | Medum | Alaa Al-Smadi | The BRD has been shared with the stakeholders and waiting the feedback from them | TBD | TBD | TBD | The BRD has been shared with the stakeholders and waiting the feedback from them
MT2ISO | Completed |  | 100% | Completed | Completed | Medum | Alaa Al-Smadi | Completed | 6000 | 0 | 1000
AML Translator | Completed |  | 100% | Completed | Completed | Medum | Alaa Al-Smadi | Completed | 10000 | 0 | 2000
FIB – PCI DSS Project (Al Ejabi)​ | Ongoing | https://fibtask.atlassian.net/browse/FIBXPI-49 | 18% | 15/4/2026 | 15/10/2026 | High | Rudaw Abdulrahman | We have completed and sent the four requested deliverables: Cardholder Data Matrix Asset Inventory Network Diagram Data Flow Diagram Gap Assessment phase will start soon. | 35970 | 0 | Year 1: $35,970 Year 2: $37,769 Year 3: $39,657 | We have started Gap Assesment
Call Center migration | Ongoing | https://fibtask.atlassian.net/jira/software/c/projects/BMBCCM/list | 99% | 2027-01-01 | April 1st | High | Rudaw Abdulrahman | BMB Vendor: · Annual payment: $57,639 · Project implementation cost: $76,495.80 · Payment terms: 50% after equipment delivery, and 50% after project go-live. Newroz Vendor: · One-time cost: Fiber installation fees for connecting the new branch (Erbil - Ezma - Business Tower): $3,664.12 · Annual cost: $7,419.80 | 48,601,615.200IQD BMB 4,800,000 IQD Newroz | 48,601,615.200IQD BMB 810,000 IQD/ Monthly Newroz | BMB=57639$ 12x810,000 IQD Newroz | contact center successfully went live, and call testing has been completed. Both inbound and outbound calls are working perfectly. However, the Eleveo installation remains scheduled for tomorrow, after which the remaining quality management and recording features will be fully operational.
ZenHR implementation | Completed | https://fibtask.atlassian.net/jira/software/c/projects/FIBPMO/list | 100% | 2026-02-01 | 27-2-2026 | High | Rudaw Abdulrahman | Project 1: HRMS Implementation (ZenHR) Status: In Progress / Partially Deployed Budget: $27,000.00 Key Milestone Achieved: Daily operational use of core features (Employee Data, Leave, etc.). Critical Pending Item: Payroll module implementation. Next Phase: Go-live and validation of Payroll. Project 2: Attendance System Deployment Status: Completed Budget: $3,825.75 Key Milestone Achieved: Hardware installation and system integration completed. Subscription & Licensing Update (Complete) Change: +338 employees added to the system. Status: Completed Budget/Amount: $5,070 (prorated charge for January 2026) Effective Date: January 2026 | 32160 | 0 | 32160
\
Process Enhancement and Automation | Ongoing | https://fibtask.atlassian.net/jira/software/c/projects/FIBPEAP/list | 50% | 1.10.2025 | TBD | Medium | Ezzat Zalzala | Almost all departments sent their BRDs, except for HR due to manager changment, now we started with the development phase and started with Treasury department. | $0 (In-House) | In-House | In-House | All departments are within the development phase, except for operations and HR, which will be next week.
Centralized data warehouse - Gap Analysis | Ongoing | https://fibtask.atlassian.net/jira/software/c/projects/FIBGAP/list | 25% | 1.3.2025 | TBD | Medium | Ezzat Zalzala | - Gap Analysis – Phase I: Completed Data collection across all business functions was carried out by Beye Group. As the main outcome of Phase I, the identified gaps were documented along with their corresponding remediation plans. - Gap Analysis – Phase II: In Progress Following Beye Group’s final proposal on October 9, with a total cost of $800,064 (including hardware, system implementation, and remediation activities), the proposal was declined. Two weeks ago, a final agreement was reached with Mr. Aland and Mr. Hazim to execute the remediation plans in-house, and this work is currently underway. - Updates : Awaiting feedback from Kak Onel for the data collected and sent to Beye group for their results as identification of gaps, after re-analysing their data we will dive deeper into their insights and understand clearly whether their remedy plans placed reasonably and tailored to our bank. - Budget: To be determined upon receiving final confirmation from Mr. Hazim. | $0 (In-House) | In-House | In-House | The tasks related to Goran team is on hold while remaining gaps are being progressed.
PEPS - EY assessment | Ongoing |  | 5% | 2026-06-04 |  | High | Waael Al-Qadhi | To implement the controls that cover the EY assesment report through the compliance and development teams. | 0$ | 0$ | In-House | A meeting scheduled on next Sunday with Ibrahim, Hazim, abdulrhman alhayek and Khalid to discuss the dormancy, onboarding documents and the timeline
Gas Station | Cpmpleted | https://fibtask.atlassian.net/browse/FIBXPI-749 | 100% | 13.1.2026 | 21.4.2026 | Medium | Ezzat Zalzala | The project completed |  |  |  | The project is complete.
Compliance Predator | Ongoing | https://fibtask.atlassian.net/jira/software/c/projects/FIBCGPI/boards/98 | 95% | 1.1.2025 | 1.5.2026 | High | Ali Zirak | Compliance System monitoring, is on Implementation stage 105,000$ has been paid for support and implementation and 200,000$ has been paid for annual license while 45000$ remiainig | 105,000$ + (200,000$ first Year license) 200,000$ Second Year license | 45000$ | 200000 | Project Status: The first round of testing has been conducted and is currently being reviewed by the Compliance team. Progress continued on the final Predator testing cycle required before go-live. To enable Compliance testing with a clean and controlled dataset, all existing data in Predator needs to be deleted before uploading the new prepared data. The required data has now been prepared and is ready to be uploaded into Predator for the next testing round. In parallel, the System Admin team increased the stage environment capacity by adding 8 additional cores, which should help support the testing activity and improve environment readiness. Once the existing data is removed and the new data is uploaded, Compliance will proceed with reviewing the transactions, validating the triggered alerts, and confirming whether the system is ready from an operational and compliance perspective before go-live.

## Finanical
ATMS Project
| Trail Balance As of |  | 2025-11-27 | 158215
| LED_CODE | LED_Name | SUB_ACCT_CODE | Tranx Date | Paid Payments | Equavalant Balance | Des
| 1291 | مشاريع تحت التنفيذ | 11 | 2025-03-13 | 72500 | IQD 94,975,000.00 | شراء 5 اي تي ام مواقع جديدة شمال العراق
| 1291 | مشاريع تحت التنفيذ | 11 | 2025-03-18 | 35750 | IQD 46,832,500.00 | شراء اجهزة اي تي ام عدد 5 اخرى الى مواقع جديدة
| 1291 | مشاريع تحت التنفيذ | 11 | 2025-07-22 | 35750 | IQD 46,832,500.00 | الدفعة الثانية من كلفة شراء اجهزة اي تي ام عدد 5 اخرى الى مواقع جديدة
| 1291 | مشاريع تحت التنفيذ | 11 | 2025-08-27 | 14215 | IQD 18,621,650.00 | اي تي ام من شركة انفوتك عدد واحد من حساب 1663-28 بتاريخ 25/11/2024
| Total Balance |  |  |  | 158215 | IQD 207,261,650.00
XPI Project
WIP
NSY
Done
ON Hold
1 | Approved | Budget | Actual (Paid) | Committed | Notes | Doc Link
| Bill Payment | 161000 | $ - | 161000 | NSY
| EPG [ Payment Gateway ] | 100000 | $ - | 100000 | NSY
| PCI Certification | 100000 | 55650 | 44350 | WIP | 55,643.98 $ . دفعات مقدمة عن مشروع فيزا 2024 2025.pdf
| Oracle Data Base License | 750000 | 722719 | 27281 | WIP | 935,765,265,.300 دفعة شركة اوراكل عن مشروع اكس باي.pdf | فاتورة اوراكل $4,197.pdf
| NewLand TMS | 86000 | 51600 | 34400 | WIP
| CMS | 400000 | 175000 | 225000 | WIP
| Professional Services l XPI | 300000 | 175800 | 124200 | WIP | ..\..\Downloads\فاتورة شركة جي بيمنت $ 800.pdf
| HSM | 283000 | 283000 | $ - | NSY | فاتورة بي ام بي دفعة ثانية واخيرة عن مشروع فيزا $141,583.pdf
| DC & DR Infrastructure HW. | 650000 | 600559 | 49441 | WIP | فاتورة شركة بي ام بي الدفعة الثانية عن مشروع فيزا هارد وير 381,377,040.pdf
| POS HW (4k over 1year) | 400000 | $ - | 400000 | NSY
| END Point Implementation VAP + MIP / DC | 175000 | 45362 | 129638 | WIP | فاتورة شركة ادفكتس عن مشروع فيزا 17,980,000.pdf | فاتورة شركة ايرثلنك عن مشروع فيزا 31,444,000.pdf | فاتورة شركة حلم المستقبل 10,000,000.pdf
| END Point Implementation VAP + MIP / DR | 175000 | $ - | 175000 | NSY
| Master Card Acquiring License | 120000 | 26460 | 93540 | WIP | فاتورة شركة فايم عن مشروع فيزا $ 15,600.pdf | ..\..\Downloads\فاتورة شركة فايم عن مشروع فيزا $ 5,050.pdf
| Duty Travel | 200000 | 107830 | 92170 | WIP
| Developer cost | 323664 | $ - | 323664 | NSY
| Our own data center | 250000 | 246357 | 3643 | WIP | https://fibadmin.sharepoint.com/:b:/s/FinanceShared/ERPN8bL0BjxNmiHQG6cAv04BrGQPup48B4gdZBFszocr-A?e=UWiBvX
2 | Opex | Budget | Actual (Paid) | Committed
| XPI Maintenance annual cost | 110000 |  | 110000 | NSY
| Master Card Acquiring License Annual Fee | 50000 |  | 50000 | On Hold
| Visa Acquiring License Annual Fee | 50000 |  | 50000 | On Hold
| HSM Maintenance | 20000 |  | 20000 | NSY
| Salaries | 1179600 | 116031 | 1063569 | WIP
| Visa licensing fees fees | 230000 |  | 230000 | On Hold
| License ORACEL | 150000 | 130268 | 19732 | WIP
| TMS | 17000 |  | 17000 | NSY
| Visa fees reporting based | 4000000 |  | 4000000 | On Hold